## Summary
Concrete acceptance summary, project 2417, Harbor View Parking Structure, placements of August and September 2026
Prepared for the engineer of record and the owner's representative under Section 03 30 00, 3.12.1; summary prepared October 21, 2026
Finding | M-4000 | M-6000 | Read from
Project number | 2417 | 2417 | Placement log and break record
Specified strength f'c (psi) | 4000 | 6000 | Parameters
Strength tests used for acceptance | 12 | 10 | Acceptance tabs
Sets cast and not used for acceptance | 6 | 0 | Samples and Tests
Lowest strength test (psi) | 3460 | 5400 | Acceptance tabs
Moving averages of three below f'c, criterion (a) | 3 | 5 | Acceptance tabs
Lowest moving average of three (psi) | 3706.7 | 5860 | Acceptance tabs
Tests below f'c by more than the allowance, criterion (b) | 2 | 0 | Acceptance tabs
Placements with a test failing criterion (b) | P-05 P-06 | None | Acceptance tabs
Acceptance under 3.11.1 | Does not meet 3.11.1 | Does not meet 3.11.1 | Acceptance tabs
What 3.11.2 calls for next | Report each placement to the engineer of record; the contractor investigates under ACI 318-19 section 26.12.6, which may include cores under ASTM C42, and takes steps to increase the average of subsequent strength tests | The contractor takes steps to increase the average of subsequent strength tests; no placement goes to investigation | 3.11.2
Core average floor, 85 percent of f'c (psi) | 3400 | 5100 | Parameters
Core single floor, 75 percent of f'c (psi) | 3000 | 4500 | Parameters
Sampling, sets and notes, both mixtures
Days on which a mixture was sampled short of 3.10.1 | 7 |  | Sampling
Days short, listed | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000; 09/11 M-4000 |  | Sampling
Sets cast and not used, both mixtures | 6 |  | Samples and Tests
Tests with a within-test range note | 2 |  | Tests
Tests used that carry a curing note | 3 |  | Tests
Samples outside a fresh concrete limit | 3 |  | Tests
Cylinders on the break record | 110 |  | Cylinders
Every value on this page reads from the tab named beside it. The Cylinders tab computes each cylinder strength and age from the break record and the field sampling log, and the Tests, Acceptance and Sampling tabs read from it.

## Parameters
Parameters and conventions the summary applies, from Section 03 30 00, LP-07 and the project file
Parameter | M-4000 | M-6000 | Source
Specified strength f'c (psi) | 4000 | 6000 | Section 03 30 00, 2.4
Criterion (b) allowance below f'c (psi) | 500 | 600 | 3.11.1(b)
Core average floor, 85 percent of f'c (psi) | 3400 | 5100 | 3.11.2
Core single floor, 75 percent of f'c (psi) | 3000 | 4500 | 3.11.2
Slump, low limit (in) | 3 | 5 | 2.4
Slump, high limit (in) | 5 | 7 | 2.4
Air content, low limit (percent) | 4.5 | 2 | 2.4
Air content, high limit (percent) | 7.5 | 4 | 2.4
Maximum concrete temperature (F) | 90 | 90 | 2.4
Approved mix design, Kolstad Ready Mix | 4A317 | 6S224 | 2.4
Parameter | Value |  | Source
Cubic yards per strength test | 150 |  | 3.10.1
Square feet of slab or wall surface per strength test | 5000 |  | 3.10.1
Cylinders per test, 6 by 12 | 2 |  | 3.10.2
Cylinders per test, 4 by 8 | 3 |  | 3.10.2
Test age (hours), 28 days | 672 |  | 3.10.3
Age tolerance (hours) either side | 20 |  | 3.10.3; LP-07 1.2
Range limit, two 6 by 12 cylinders (percent) | 6.6 |  | 3.10.4; LP-07 2.3
Range limit, three 4 by 8 cylinders (percent) | 10.6 |  | 3.10.4; LP-07 2.3
Initial curing, low limit (F) | 60 |  | 3.10.6
Initial curing, high limit (F) | 80 |  | 3.10.6
Initial curing, longest period (hours) | 48 |  | 3.10.6
Rounding unit for strengths (psi) | 10 |  | 3.10.3; LP-07 2.2
Hours in a day | 24 |  | Age and curing period conversion
Minutes in a day | 1440 |  | Age and curing period conversion
Earliest age reported for information (days) | 25 |  | Cylinders broken near 28 days
Latest age reported for information (days) | 31 |  | Cylinders broken near 28 days
Conventions the figures rest on |  |  | Source
Age is reckoned in hours from the time of molding on the field sampling log to the time of the break, and a cylinder counts at 28 days when it is within 20 hours of 672 hours. |  |  | 3.10.3; LP-07 1.2
Each cylinder strength is the load over the area from the average of the two measured diameters, with pi carried in full and the average diameter carried without rounding. |  |  | 3.10.3; LP-07 2.1
A cylinder with a defect written on the break record is discarded, and the reserve cylinder broken at 28 days enters the test in its place. |  |  | 3.10.5
Sets molded from one delivery ticket are one sample and make one strength test, and one truck batched at one time is one delivery ticket whatever number was written on the line. |  |  | 3.10.2
L. Brandvold's lines are on the 12 hour clock, and each time is read into the hours the placement log gives for the placement. |  |  | LP-07 1.4; placement log
The cast date of a set is the date the placement log gives for the placement it was molded from. |  |  | Placement log; laboratory memo item 3
The box thermometer is read as a low and a high, whichever was written first. |  |  | LP-07 1.5
Field cured cylinders are reported apart and are not strength tests. |  |  | 3.10.6
A test is set aside only on the written direction of the engineer of record. |  |  | 3.10.7
Tests run in the order their samples were molded, by date and time, and the first two averages of each mixture take in the last two July tests used for acceptance, as corrected by the laboratory's letter of September 15. |  |  | 3.11.3; July transmittal
A moving average equal to f'c meets criterion (a), and a test below f'c by exactly the allowance meets criterion (b). |  |  | 3.11.1
The 10 percent allowance of criterion (b) applies to M-6000, because its f'c exceeds 5,000 psi. |  |  | 3.11.1(b)
Sampling is judged on the day's total of each mixture across every placement of the day, and it is met only by strength tests used for acceptance. |  |  | 3.10.1

## Placements
Placement log, placement_log_2417.csv, line for line, with the mixture of each placement
PLACEMENT_ID | DATE | ELEMENT | MIX_DESIGN | CUBIC_YARDS | SURFACE_AREA_SF | START | FINISH | MIXTURE
P-01 | 08/03/2026 | Level 2 deck bay A | 4A317 | 104 | 4810 | 06:40 | 11:25 | M-4000
P-02 | 08/05/2026 | Level 2 deck bay B | 4A317 | 98 | 4540 | 06:55 | 11:10 | M-4000
P-03 | 08/05/2026 | Level 2 stair landings | 4A317 | 9 | 410 | 11:30 | 12:20 | M-4000
P-04 | 08/06/2026 | Columns Level 2 grid 1 to 4 | 6S224 | 38 |  | 08:50 | 12:05 | M-6000
P-05 | 08/10/2026 | Level 2 deck bays C and D | 4A317 | 318 | 14720 | 05:50 | 16:10 | M-4000
P-06 | 08/12/2026 | Level 3 deck bay A | 4A317 | 101 | 4670 | 06:45 | 11:35 | M-4000
P-07 | 08/13/2026 | Columns Level 2 grid 5 to 8 | 6S224 | 41 |  | 08:20 | 11:50 | M-6000
P-08 | 08/14/2026 | Level 3 deck bay B | 4A317 | 112 | 5180 | 06:30 | 11:55 | M-4000
P-09 | 08/15/2026 | Ramp slab south lower run | 4A317 | 150 | 4860 | 05:55 | 12:40 | M-4000
P-10 | 08/17/2026 | Level 3 deck bay C | 4A317 | 151 | 6990 | 06:35 | 13:05 | M-4000
P-11 | 08/18/2026 | Columns Level 3 grid 1 to 4 | 6S224 | 36 |  | 09:05 | 12:15 | M-6000
P-12 | 08/19/2026 | Level 3 deck bay D | 4A317 | 106 | 4905 | 06:50 | 11:45 | M-4000
P-13 | 08/20/2026 | Columns Level 3 grid 5 to 8 | 6S224 | 37 |  | 08:40 | 11:55 | M-6000
P-14 | 08/21/2026 | Ramp slab north | 4A317 | 96 | 3110 | 07:10 | 11:20 | M-4000
P-15 | 08/24/2026 | Level 4 deck bay A | 4A317 | 103 | 4770 | 09:30 | 14:50 | M-4000
P-16 | 08/24/2026 | Columns Level 3 grid 9 to 12 | 6S224 | 39 |  | 12:40 | 15:35 | M-6000
P-17 | 08/26/2026 | Level 4 deck bay B | 4A317 | 99 | 4580 | 06:35 | 11:15 | M-4000
P-18 | 08/26/2026 | Columns Level 4 grid 1 to 4 | 6S224 | 40 |  | 09:50 | 13:10 | M-6000
P-19 | 08/27/2026 | Shear walls stair 2 lifts 1 and 2 | 6S224 | 52 | 1390 | 07:30 | 12:30 | M-6000
P-20 | 08/29/2026 | Level 4 deck bay C | 4A317 | 107 | 4950 | 07:45 | 13:20 | M-4000
P-21 | 08/31/2026 | Level 4 deck bay D and crossover | 4A317 | 212 | 9810 | 06:10 | 14:35 | M-4000
P-22 | 09/02/2026 | Columns Level 4 grid 5 to 8 | 6S224 | 38 |  | 08:35 | 11:40 | M-6000
P-23 | 09/03/2026 | Shear walls stair 2 lifts 3 and 4 | 6S224 | 49 | 1310 | 07:20 | 12:10 | M-6000
P-24 | 09/08/2026 | Ramp slab south upper run | 4A317 | 88 | 2850 | 07:35 | 11:50 | M-4000
P-25 | 09/10/2026 | Shear walls stair 1 lifts 1 and 2 | 6S224 | 49 | 1310 | 07:05 | 11:30 | M-6000
P-26 | 09/10/2026 | Columns Level 4 grid 9 to 12 | 6S224 | 37 |  | 12:15 | 15:20 | M-6000
P-27 | 09/11/2026 | Level 4 curbs and islands | 4A317 | 14 | 640 | 08:10 | 10:05 | M-4000

## Samples
Field sampling log, field_sampling_log_2417.csv, one line per set, as read against the placement log and the project file
SET_NO | FIELD_TECH | DATE_CAST | TIME_MOLDED | LOCATION | TICKET_NO | MIX_DESIGN | MIXTURE | PLACEMENT_ID | SLUMP_IN | AIR_PCT | CONC_TEMP_F | FRESH_CONCRETE | CYL_SIZE | INITIAL_CURING | CURING_CLASS | BOX_LOW_F | BOX_HIGH_F | PICKED_UP_DATE | PICKED_UP_TIME | HOURS_IN_BOX | CURING_NOTE | ENGINEER_DIRECTION | MOLDED_SERIAL | USED | READING_OF_THE_FIELD_LOG
S-101 | R. Okafor | 08/03/2026 | 07:23 | L2 deck bay A at pump | 770418 | 4A317 | M-4000 | P-01 | 4.25 | 6.2 | 74 | Within 2.4 | 6x12 | Box 1 | Standard | 63 | 77 | 08/04/2026 | 07:52 | 24.48 |  |  | 46237.3076 | Yes
S-102 | R. Okafor | 08/05/2026 | 08:12 | L2 deck bay B at pump | 770653 | 4A317 | M-4000 | P-02 | 5 | 5.8 | 76 | Within 2.4 | 6x12 | Box 1 | Standard | 64 | 78 | 08/06/2026 | 07:34 | 23.37 |  |  | 46239.3417 | Yes
S-103 | R. Okafor | 08/10/2026 | 06:52 | L2 deck C/D north pump | 771106 | 4A317 | M-4000 | P-05 | 4 | 6.4 | 71 | Within 2.4 | 6x12 | Box 1 | Standard | 62 | 76 | 08/11/2026 | 06:56 | 24.07 |  |  | 46244.2861 | No
S-104 | R. Okafor | 08/10/2026 | 10:18 | L2 deck C/D north pump | 771131 | 4A317 | M-4000 | P-05 | 4.25 | 6.7 | 77 | Within 2.4 | 6x12 | Box 1 | Standard | 62 | 76 | 08/11/2026 | 06:56 | 20.63 |  |  | 46244.4292 | No
S-105 | R. Okafor | 08/12/2026 | 07:38 | L3 deck bay A at pump | 771342 | 4A317 | M-4000 | P-06 | 5.25 | 5.9 | 81 | Outside 2.4 | 6x12 | Box 1 | Standard | 64 | 78 | 08/13/2026 | 07:47 | 24.15 |  |  | 46246.3181 | Yes
S-106 | R. Okafor | 08/14/2026 | 07:17 | L3 deck bay B at pump | 771587 | 4A317 | M-4000 | P-08 | 4.75 | 7.8 | 80 | Outside 2.4 | 6x12 | Box 1 | Standard | 63 | 79 | 08/17/2026 | 09:41 | 74.4 | Initial curing period over 48 hours |  | 46248.3035 | Yes
S-107 | R. Okafor | 08/14/2026 | 09:48 | L3 deck bay B at pump | 771604 | 4A317 | M-4000 | P-08 | 4.5 | 6.6 | 82 | Within 2.4 | 6x12 | On L3 deck at bay B under burlap and poly | Field |  |  | 09/11/2026 | 06:41 |  |  |  | 46248.4083 | No
S-108 | R. Okafor | 08/15/2026 | 06:43 | South ramp lower run at chute | 771688 | 4A317 | M-4000 | P-09 | 4 | 6.1 | 69 | Within 2.4 | 6x12 | Box 2 | Standard | 62 | 75 | 08/16/2026 | 07:36 | 24.88 |  |  | 46249.2799 | Yes
S-109 | R. Okafor | 08/17/2026 | 08:06 | L3 deck bay C at pump | 771842 | 4A317 | M-4000 | P-10 | 4.25 | 7.5 | 75 | Within 2.4 | 6x12 | Box 1 | Standard | 63 | 77 | 08/19/2026 | 07:51 | 47.75 |  |  | 46251.3375 | Yes
S-110 | R. Okafor | 08/19/2026 | 08:21 | L3 deck bay D at pump | 772071 | 4A317 | M-4000 | P-12 | 4.5 | 5.6 | 73 | Within 2.4 | 6x12 | Box 1 | Standard | 62 | 74 | 08/20/2026 | 07:18 | 22.95 |  |  | 46253.3479 | Yes
S-111 | R. Okafor | 08/21/2026 | 09:13 | North ramp at chute | 772316 | 4A317 | M-4000 | P-14 | 4 | 6 | 72 | Within 2.4 | 4x8 | Box 2 | Standard | 61 | 73 | 08/22/2026 | 08:16 | 23.05 |  |  | 46255.384 | No
S-112 | R. Okafor | 08/24/2026 | 13:44 | L4 deck bay A at pump | 772569 | 4A317 | M-4000 | P-15 | 4.5 | 6.3 | 79 | Within 2.4 | 6x12 | Box 1 | Standard | 63 | 80 | 08/25/2026 | 07:29 | 17.75 |  |  | 46258.5722 | Yes
S-113 | R. Okafor | 08/26/2026 | 07:19 | L4 deck bay B at pump | 772784 | 4A317 | M-4000 | P-17 | 3.75 | 5.7 | 71 | Within 2.4 | 6x12 | Box 2 | Standard | 66 | 91 | 08/27/2026 | 16:22 | 33.05 | Initial curing temperature outside 60 to 80 F | Set aside, letter of October 2, 2026 | 46260.3049 | No
S-114 | R. Okafor | 08/29/2026 | 11:32 | L4 deck bay C at pump | 773127 | 4A317 | M-4000 | P-20 | 4.25 | 6.5 | 90 | Within 2.4 | 6x12 | Box 1 | Standard | 66 | 79 | 08/31/2026 | 06:33 | 43.02 |  |  | 46263.4806 | No | Date written 08/28/2026. The placement log has bay C on 08/29/2026, a Saturday, and the memo counts it among the Saturday placements.
S-115 | R. Okafor | 08/31/2026 | 11:22 | L4 deck bay D at pump | 773295 | 4A317 | M-4000 | P-21 | 4.5 | 6 | 77 | Within 2.4 | 6x12 | Box 1 | Standard | 64 | 78 | 09/01/2026 | 07:14 | 19.87 |  |  | 46265.4736 | Yes
S-116 | R. Okafor | 09/08/2026 | 08:31 | South ramp upper run at chute | 773902 | 4A317 | M-4000 | P-24 | 3.5 | 5.5 | 64 | Within 2.4 | 6x12 | Box 2 | Standard | 57 | 74 | 09/09/2026 | 07:42 | 23.18 | Initial curing temperature outside 60 to 80 F |  | 46273.3549 | Yes
S-201 | L. Brandvold | 08/06/2026 | 09:36 | Cols L2 grid 1-4 at bucket | 770812 | 6S224 | M-6000 | P-04 | 6 | 3.1 | 78 | Within 2.4 | 4x8 | Box 2 | Standard | 65 | 78 | 08/07/2026 | 07:06 | 21.5 |  |  | 46240.4 | Yes
S-202 | L. Brandvold | 08/10/2026 | 14:37 | L2 deck C/D south pump | 771163 | 4A317 | M-4000 | P-05 | 4.75 | 5.4 | 83 | Within 2.4 | 6x12 | Box 2 | Standard | 65 | 79 | 08/11/2026 | 07:11 | 16.57 |  |  | 46244.609 | Yes | Written 2:37 with the batch at 1:47. The placement ran 05:50 to 16:10, which puts the molding at 14:37.
S-203 | L. Brandvold | 08/13/2026 | 09:04 | Cols L2 grid 5-8 at bucket | 771469 | 6S224 | M-6000 | P-07 | 5.5 | 2.8 | 77 | Within 2.4 | 4x8 | Box 2 | Standard | 64 | 77 | 08/14/2026 | 07:27 | 22.38 |  |  | 46247.3778 | Yes
S-204 | L. Brandvold | 08/18/2026 | 09:53 | Cols L3 grid 1-4 at bucket | 771955 | 6S224 | M-6000 | P-11 | 7 | 3.3 | 79 | Within 2.4 | 4x8 | Box 2 | Standard | 60 | 77 | 08/19/2026 | 08:04 | 22.18 |  |  | 46252.4118 | Yes | Thermometer written 77/60 with the high first. The low of 60 F is inside the range.
S-205 | L. Brandvold | 08/19/2026 | 08:27 | L3 deck bay D at pump | 772071 | 4A317 | M-4000 | P-12 | 4.5 | 5.6 | 73 | Within 2.4 | 6x12 | Box 1 | Standard | 62 | 74 | 08/20/2026 | 07:18 | 22.85 |  |  | 46253.3521 | Yes | Ticket written 772017. Truck 33 batched at 07:33 is the load of ticket 772071 on the S-110 line.
S-206 | L. Brandvold | 08/20/2026 | 09:26 | Cols L3 grid 5-8 at bucket | 772203 | 6S224 | M-6000 | P-13 | 6.5 | 3.4 | 78 | Within 2.4 | 4x8 | Box 2 | Standard | 63 | 76 | 08/21/2026 | 07:39 | 22.22 |  |  | 46254.3931 | Yes
S-207 | L. Brandvold | 08/24/2026 | 13:52 | Cols L3 grid 9-12 at bucket | 772531 | 6S224 | M-6000 | P-16 | 6.25 | 2.9 | 81 | Within 2.4 | 4x8 | Box 2 | Standard | 62 | 75 | 08/25/2026 | 07:43 | 17.85 |  |  | 46258.5778 | Yes | Written 1:52 with the batch at 1:09. The placement ran 12:40 to 15:35, which puts the molding at 13:52.
S-208 | L. Brandvold | 08/26/2026 | 10:41 | Cols L4 grid 1-4 at bucket | 772809 | 6S224 | M-6000 | P-18 | 5.75 | 3 | 76 | Within 2.4 | 4x8 | Box 2 | Standard | 66 | 91 | 08/27/2026 | 16:22 | 29.68 | Initial curing temperature outside 60 to 80 F |  | 46260.4451 | Yes | Thermometer written 91/66 with the high first. Picked up with S-113 at 16:22, written 4:22.
S-209 | L. Brandvold | 08/27/2026 | 08:14 | Stair 2 shear walls lift 1 at pump | 772934 | 6S224 | M-6000 | P-19 | 6.25 | 2.6 | 70 | Within 2.4 | 4x8 | Box 1 | Standard | 63 | 76 | 08/28/2026 | 07:09 | 22.92 |  |  | 46261.3431 | Yes
S-210 | L. Brandvold | 08/31/2026 | 06:57 | L4 deck bay D at pump | 773248 | 4A317 | M-4000 | P-21 | 4 | 6.2 | 68 | Within 2.4 | 6x12 | Box 1 | Standard | 64 | 78 | 09/01/2026 | 07:14 | 24.28 |  |  | 46265.2896 | Yes
S-211 | L. Brandvold | 09/02/2026 | 09:19 | Cols L4 grid 5-8 at bucket | 773471 | 6S224 | M-6000 | P-22 | 6 | 4.2 | 75 | Outside 2.4 | 4x8 | Box 2 | Standard | 62 | 74 | 09/03/2026 | 07:01 | 21.7 |  |  | 46267.3882 | Yes
S-212 | L. Brandvold | 09/03/2026 | 08:07 | Stair 2 shear walls lift 3 at pump | 773586 | 6S224 | M-6000 | P-23 | 6.75 | 3.6 | 71 | Within 2.4 | 4x8 | Box 1 | Standard | 61 | 73 | 09/04/2026 | 07:32 | 23.42 |  |  | 46268.3382 | Yes
S-213 | L. Brandvold | 09/10/2026 | 12:52 | Cols L4 grid 9-12 at bucket | 774119 | 6S224 | M-6000 | P-26 | 5.75 | 2.7 | 69 | Within 2.4 | 4x8 | Box 2 | Standard | 61 | 72 | 09/11/2026 | 07:21 | 18.48 |  |  | 46275.5361 | Yes | Written 12:52 and read as 12:52 in the afternoon, inside the placement hours of 12:15 to 15:20.

## Cylinders
Every cylinder on the break record, cylinder_breaks_2417.csv, one line per cylinder, with its age and computed strength
CYLINDER | SET_NO | MARK | TICKET_NO | TEST_DATE | TEST_TIME | DIA1_IN | DIA2_IN | MAX_LOAD_LBF | FRACTURE | DEFECT_ON_RECORD | AGE_HOURS | AGE_DAYS | WITHIN_20_HOURS_OF_28_DAYS | CURING_CLASS | AREA_SQ_IN | STRENGTH_PSI | ENTERS_TEST
S-101-A | S-101 | A | 770418 | 08/10/2026 | 09:09 | 5.98 | 6 | 85971 | Type 2 | No | 169.77 | 7.07 | No | Standard | 28.1802 | 3050 | No
S-101-B | S-101 | B | 770418 | 08/31/2026 | 10:12 | 6.02 | 6.04 | 125397 | Type 4 | No | 674.82 | 28.12 | Yes | Standard | 28.5578 | 4390 | Yes
S-101-C | S-101 | C | 770418 | 08/31/2026 | 10:19 | 6.01 | 6.01 | 116595 | Type 2 | No | 674.93 | 28.12 | Yes | Standard | 28.3687 | 4110 | Yes
S-101-D | S-101 | D | 770418 | 09/28/2026 | 14:06 | 6.01 | 6.01 | 131625 | Type 3 | No | 1350.72 | 56.28 | No | Standard | 28.3687 | 4640 | No
S-102-A | S-102 | A | 770653 | 08/12/2026 | 08:36 | 6 | 6 | 88767 | Type 3 | No | 168.4 | 7.02 | No | Standard | 28.2743 | 3140 | No
S-102-B | S-102 | B | 770653 | 09/02/2026 | 09:48 | 6.01 | 6.01 | 126828 | Type 2 | No | 673.6 | 28.07 | Yes | Standard | 28.3687 | 4470 | Yes
S-102-C | S-102 | C | 770653 | 09/02/2026 | 09:57 | 6 | 5.98 | 123712 | Type 3 | No | 673.75 | 28.07 | Yes | Standard | 28.1802 | 4390 | Yes
S-102-D | S-102 | D | 770653 | 09/30/2026 | 14:33 | 6.02 | 5.98 | 134586 | Type 2 | No | 1350.35 | 56.26 | No | Standard | 28.2743 | 4760 | No
S-103-A | S-103 | A | 771106 | 08/17/2026 | 08:44 | 5.98 | 6 | 83429 | Type 2 | No | 169.87 | 7.08 | No | Standard | 28.1802 | 2960 | No
S-103-B | S-103 | B | 771106 | 09/08/2026 | 08:35 | 5.99 | 5.97 | 116854 | Type 2 | No | 697.72 | 29.07 | No | Standard | 28.0862 | 4160 | No
S-103-C | S-103 | C | 771106 | 09/08/2026 | 08:42 | 6.02 | 6 | 115719 | Type 2 | No | 697.83 | 29.08 | No | Standard | 28.3687 | 4080 | No
S-103-D | S-103 | D | 771106 | 10/05/2026 | 11:35 | 5.97 | 5.97 | 125131 | Type 2 | No | 1348.72 | 56.2 | No | Standard | 27.9923 | 4470 | No
S-104-A | S-104 | A | 771131 | 08/17/2026 | 10:10 | 6 | 6 | 84560 | Type 2 | No | 167.87 | 6.99 | No | Standard | 28.2743 | 2990 | No
S-104-B | S-104 | B | 771131 | 09/08/2026 | 08:50 | 5.99 | 6.01 | 113697 | Type 1 | No | 694.53 | 28.94 | No | Standard | 28.2743 | 4020 | No
S-104-C | S-104 | C | 771131 | 09/08/2026 | 08:57 | 6.01 | 6.01 | 116281 | Type 1 | No | 694.65 | 28.94 | No | Standard | 28.3687 | 4100 | No
S-104-D | S-104 | D | 771131 | 10/05/2026 | 09:34 | 6.01 | 6.01 | 125919 | Type 3 | No | 1343.27 | 55.97 | No | Standard | 28.3687 | 4440 | No
S-105-A | S-105 | A | 771342 | 08/19/2026 | 08:32 | 6 | 6.02 | 70091 | Type 2 | No | 168.9 | 7.04 | No | Standard | 28.3687 | 2470 | No
S-105-B | S-105 | B | 771342 | 09/09/2026 | 10:31 | 5.99 | 5.97 | 101657 | Type 3 | No | 674.88 | 28.12 | Yes | Standard | 28.0862 | 3620 | Yes
S-105-C | S-105 | C | 771342 | 09/09/2026 | 10:38 | 5.99 | 5.97 | 93827 | Type 3 | No | 675 | 28.13 | Yes | Standard | 28.0862 | 3340 | Yes
S-105-D | S-105 | D | 771342 | 10/07/2026 | 10:34 | 5.99 | 6.01 | 104650 | Type 2 | No | 1346.93 | 56.12 | No | Standard | 28.2743 | 3700 | No
S-106-A | S-106 | A | 771587 | 08/21/2026 | 09:57 | 5.99 | 6.01 | 87058 | Type 4 | No | 170.67 | 7.11 | No | Standard | 28.2743 | 3080 | No
S-106-B | S-106 | B | 771587 | 09/11/2026 | 09:22 | 6.02 | 5.98 | 119562 | Type 2 | No | 674.08 | 28.09 | Yes | Standard | 28.2743 | 4230 | Yes
S-106-C | S-106 | C | 771587 | 09/11/2026 | 09:30 | 5.97 | 5.99 | 116034 | Type 1 | No | 674.22 | 28.09 | Yes | Standard | 28.0862 | 4130 | Yes
S-106-D | S-106 | D | 771587 | 10/09/2026 | 10:34 | 6 | 6 | 128388 | Type 1 | No | 1347.28 | 56.14 | No | Standard | 28.2743 | 4540 | No
S-107-A | S-107 | A | 771604 | 08/17/2026 | 08:12 | 6 | 6 | 81741 | Type 1 | No | 70.4 | 2.93 | No | Field | 28.2743 | 2890 | No
S-107-B | S-107 | B | 771604 | 08/17/2026 | 08:19 | 6.01 | 6.01 | 83696 | Type 2 | No | 70.52 | 2.94 | No | Field | 28.3687 | 2950 | No
S-107-C | S-107 | C | 771604 | 09/11/2026 | 09:41 | 6.01 | 6.01 | 97278 | Type 2 | No | 671.88 | 28 | Yes | Field | 28.3687 | 3430 | No
S-107-D | S-107 | D | 771604 | 09/11/2026 | 09:48 | 6.02 | 5.98 | 94739 | Type 4 | No | 672 | 28 | Yes | Field | 28.2743 | 3350 | No
S-108-A | S-108 | A | 771688 | 08/21/2026 | 14:32 | 6.01 | 6.03 | 85366 | Type 2 | No | 151.82 | 6.33 | No | Standard | 28.4631 | 3000 | No
S-108-B | S-108 | B | 771688 | 09/11/2026 | 15:10 | 6 | 6.02 | 121951 | Type 4 | No | 656.45 | 27.35 | Yes | Standard | 28.3687 | 4300 | Yes
S-108-C | S-108 | C | 771688 | 09/11/2026 | 15:18 | 5.99 | 6.01 | 123849 | Type 4 | No | 656.58 | 27.36 | Yes | Standard | 28.2743 | 4380 | Yes
S-109-A | S-109 | A | 771842 | 08/24/2026 | 14:43 | 6.01 | 6.01 | 87126 | Type 3 | No | 174.62 | 7.28 | No | Standard | 28.3687 | 3070 | No
S-109-B | S-109 | B | 771842 | 09/14/2026 | 10:03 | 6 | 6.02 | 120848 | Type 4 | No | 673.95 | 28.08 | Yes | Standard | 28.3687 | 4260 | Yes
S-109-C | S-109 | C | 771842 | 09/14/2026 | 10:10 | 6.01 | 6.01 | 118580 | Type 2 | No | 674.07 | 28.09 | Yes | Standard | 28.3687 | 4180 | Yes
S-110-A | S-110 | A | 772071 | 08/26/2026 | 13:49 | 6.04 | 6.02 | 73361 | Type 2 | No | 173.47 | 7.23 | No | Standard | 28.5578 | 2570 | No
S-110-B | S-110 | B | 772071 | 09/16/2026 | 09:37 | 6.02 | 6.04 | 98538 | Type 2 | No | 673.27 | 28.05 | Yes | Standard | 28.5578 | 3450 | Yes
S-110-C | S-110 | C | 772071 | 09/16/2026 | 09:44 | 6 | 6 | 99208 | Type 3 | No | 673.38 | 28.06 | Yes | Standard | 28.2743 | 3510 | Yes
S-111-A | S-111 | A | 772316 | 08/28/2026 | 10:33 | 4.02 | 4 | 38409 | Type 2 | No | 169.33 | 7.06 | No | Standard | 12.6293 | 3040 | No
S-111-B | S-111 | B | 772316 | 09/18/2026 | 10:44 | 4.02 | 4.02 | 54079 | Type 2 | No | 673.52 | 28.06 | Yes | Standard | 12.6923 | 4260 | Yes
S-111-C | S-111 | C | 772316 | 09/18/2026 | 10:52 | 4 | 4.02 | 53295 | Type 3 | No | 673.65 | 28.07 | Yes | Standard | 12.6293 | 4220 | Yes
S-111-D | S-111 | D | 772316 | 09/18/2026 | 10:58 | 4.01 | 3.99 | 48885 | Type 6 | Yes | 673.75 | 28.07 | Yes | Standard | 12.5664 | 3890 | No
S-111-E | S-111 | E | 772316 | 08/28/2026 | 10:41 | 4.02 | 4 | 38506 | Type 2 | No | 169.47 | 7.06 | No | Standard | 12.6293 | 3050 | No
S-112-A | S-112 | A | 772569 | 08/31/2026 | 13:16 | 5.99 | 6.01 | 84271 | Type 2 | No | 167.53 | 6.98 | No | Standard | 28.2743 | 2980 | No
S-112-B | S-112 | B | 772569 | 09/22/2026 | 08:02 | 6 | 6 | 122447 | Type 4 | No | 690.3 | 28.76 | Yes | Standard | 28.2743 | 4330 | Yes
S-112-C | S-112 | C | 772569 | 09/22/2026 | 08:08 | 6.01 | 5.99 | 120139 | Type 2 | No | 690.4 | 28.77 | Yes | Standard | 28.2743 | 4250 | Yes
S-113-A | S-113 | A | 772784 | 09/02/2026 | 10:53 | 6 | 6 | 91317 | Type 1 | No | 171.57 | 7.15 | No | Standard | 28.2743 | 3230 | No
S-113-B | S-113 | B | 772784 | 09/23/2026 | 09:16 | 6.02 | 6 | 125704 | Type 2 | No | 673.95 | 28.08 | Yes | Standard | 28.3687 | 4430 | Yes
S-113-C | S-113 | C | 772784 | 09/23/2026 | 09:25 | 5.98 | 6 | 122561 | Type 2 | No | 674.1 | 28.09 | Yes | Standard | 28.1802 | 4350 | Yes
S-114-A | S-114 | A | 773127 | 09/04/2026 | 08:17 | 5.99 | 5.99 | 87075 | Type 2 | No | 140.75 | 5.86 | No | Standard | 28.1802 | 3090 | No
S-114-B | S-114 | B | 773127 | 09/25/2026 | 09:15 | 6 | 6.02 | 122874 | Type 2 | No | 645.72 | 26.91 | No | Standard | 28.3687 | 4330 | No
S-114-C | S-114 | C | 773127 | 09/25/2026 | 09:21 | 6.04 | 6.02 | 121919 | Type 1 | No | 645.82 | 26.91 | No | Standard | 28.5578 | 4270 | No
S-115-A | S-115 | A | 773295 | 09/08/2026 | 10:54 | 5.97 | 5.97 | 86757 | Type 2 | No | 191.53 | 7.98 | No | Standard | 27.9923 | 3100 | No
S-115-B | S-115 | B | 773295 | 09/28/2026 | 13:24 | 6 | 6 | 122694 | Type 2 | No | 674.03 | 28.08 | Yes | Standard | 28.2743 | 4340 | Yes
S-115-C | S-115 | C | 773295 | 09/28/2026 | 13:30 | 6.02 | 6 | 120871 | Type 1 | No | 674.13 | 28.09 | Yes | Standard | 28.3687 | 4260 | Yes
S-116-A | S-116 | A | 773902 | 09/15/2026 | 08:24 | 6 | 6 | 88789 | Type 1 | No | 167.88 | 7 | No | Standard | 28.2743 | 3140 | No
S-116-B | S-116 | B | 773902 | 10/06/2026 | 09:52 | 6.01 | 5.99 | 123002 | Type 4 | No | 673.35 | 28.06 | Yes | Standard | 28.2743 | 4350 | Yes
S-116-C | S-116 | C | 773902 | 10/06/2026 | 09:59 | 5.97 | 5.99 | 119891 | Type 2 | No | 673.47 | 28.06 | Yes | Standard | 28.0862 | 4270 | Yes
S-201-A | S-201 | A | 770812 | 08/13/2026 | 09:43 | 4.02 | 4 | 52147 | Type 1 | No | 168.12 | 7.01 | No | Standard | 12.6293 | 4130 | No
S-201-B | S-201 | B | 770812 | 09/03/2026 | 11:08 | 4 | 4.02 | 75266 | Type 1 | No | 673.53 | 28.06 | Yes | Standard | 12.6293 | 5960 | Yes
S-201-C | S-201 | C | 770812 | 09/03/2026 | 11:15 | 3.99 | 4.01 | 74157 | Type 2 | No | 673.65 | 28.07 | Yes | Standard | 12.5664 | 5900 | Yes
S-201-D | S-201 | D | 770812 | 09/03/2026 | 11:21 | 3.97 | 4.01 | 73768 | Type 2 | No | 673.75 | 28.07 | Yes | Standard | 12.5036 | 5900 | Yes
S-201-E | S-201 | E | 770812 | 10/01/2026 | 10:17 | 4.02 | 4 | 79554 | Type 2 | No | 1344.68 | 56.03 | No | Standard | 12.6293 | 6300 | No
S-202-A | S-202 | A | 771163 | 08/17/2026 | 10:30 | 6.01 | 6.01 | 69503 | Type 2 | No | 163.88 | 6.83 | No | Standard | 28.3687 | 2450 | No
S-202-B | S-202 | B | 771163 | 09/08/2026 | 09:05 | 5.98 | 6 | 98629 | Type 2 | No | 690.47 | 28.77 | Yes | Standard | 28.1802 | 3500 | Yes
S-202-C | S-202 | C | 771163 | 09/08/2026 | 09:14 | 6.01 | 5.99 | 96663 | Type 2 | No | 690.62 | 28.78 | Yes | Standard | 28.2743 | 3420 | Yes
S-202-D | S-202 | D | 771163 | 10/05/2026 | 10:29 | 6.01 | 5.99 | 106306 | Type 1 | No | 1339.87 | 55.83 | No | Standard | 28.2743 | 3760 | No
S-203-A | S-203 | A | 771469 | 08/20/2026 | 10:09 | 4.03 | 4.01 | 56343 | Type 2 | No | 169.08 | 7.05 | No | Standard | 12.6923 | 4440 | No
S-203-B | S-203 | B | 771469 | 09/10/2026 | 10:26 | 4.04 | 4.04 | 80771 | Type 2 | No | 673.37 | 28.06 | Yes | Standard | 12.819 | 6300 | Yes
S-203-C | S-203 | C | 771469 | 09/10/2026 | 10:35 | 4.02 | 4.04 | 79587 | Type 3 | No | 673.52 | 28.06 | Yes | Standard | 12.7556 | 6240 | Yes
S-203-D | S-203 | D | 771469 | 09/10/2026 | 10:43 | 4 | 3.98 | 77631 | Type 2 | No | 673.65 | 28.07 | Yes | Standard | 12.5036 | 6210 | Yes
S-203-E | S-203 | E | 771469 | 10/08/2026 | 09:36 | 4.01 | 4.01 | 84002 | Type 1 | No | 1344.53 | 56.02 | No | Standard | 12.6293 | 6650 | No
S-204-A | S-204 | A | 771955 | 08/25/2026 | 14:31 | 4.01 | 3.99 | 52764 | Type 2 | No | 172.63 | 7.19 | No | Standard | 12.5664 | 4200 | No
S-204-B | S-204 | B | 771955 | 09/15/2026 | 11:17 | 4 | 4.02 | 77308 | Type 3 | No | 673.4 | 28.06 | Yes | Standard | 12.6293 | 6120 | Yes
S-204-C | S-204 | C | 771955 | 09/15/2026 | 11:24 | 4.02 | 4 | 76900 | Type 2 | No | 673.52 | 28.06 | Yes | Standard | 12.6293 | 6090 | Yes
S-204-D | S-204 | D | 771955 | 09/15/2026 | 11:30 | 4.04 | 4.02 | 76922 | Type 1 | No | 673.62 | 28.07 | Yes | Standard | 12.7556 | 6030 | Yes
S-205-A | S-205 | A | 772071 | 08/26/2026 | 13:27 | 6.03 | 6.03 | 71376 | Type 1 | No | 173 | 7.21 | No | Standard | 28.5578 | 2500 | No
S-205-B | S-205 | B | 772071 | 09/16/2026 | 09:53 | 5.99 | 5.99 | 100051 | Type 4 | No | 673.43 | 28.06 | Yes | Standard | 28.1802 | 3550 | Yes
S-205-C | S-205 | C | 772071 | 09/16/2026 | 10:01 | 6.02 | 5.98 | 98715 | Type 4 | No | 673.57 | 28.07 | Yes | Standard | 28.2743 | 3490 | Yes
S-206-A | S-206 | A | 772203 | 08/27/2026 | 10:11 | 3.98 | 3.98 | 50753 | Type 2 | No | 168.75 | 7.03 | No | Standard | 12.441 | 4080 | No
S-206-B | S-206 | B | 772203 | 09/17/2026 | 10:05 | 4.01 | 4.03 | 71209 | Type 2 | No | 672.65 | 28.03 | Yes | Standard | 12.6923 | 5610 | Yes
S-206-C | S-206 | C | 772203 | 09/17/2026 | 10:13 | 4.04 | 4.04 | 60240 | Type 5 | Yes | 672.78 | 28.03 | Yes | Standard | 12.819 | 4700 | No
S-206-D | S-206 | D | 772203 | 09/17/2026 | 10:20 | 3.97 | 3.99 | 69166 | Type 2 | No | 672.9 | 28.04 | Yes | Standard | 12.441 | 5560 | Yes
S-206-E | S-206 | E | 772203 | 09/17/2026 | 10:55 | 4.01 | 4.01 | 70604 | Type 2 | No | 673.48 | 28.06 | Yes | Standard | 12.6293 | 5590 | Yes
S-207-A | S-207 | A | 772531 | 08/31/2026 | 09:27 | 4.03 | 4.03 | 54840 | Type 1 | No | 163.58 | 6.82 | No | Standard | 12.7556 | 4300 | No
S-207-B | S-207 | B | 772531 | 09/22/2026 | 08:20 | 4.02 | 4 | 78058 | Type 4 | No | 690.47 | 28.77 | Yes | Standard | 12.6293 | 6180 | Yes
S-207-C | S-207 | C | 772531 | 09/22/2026 | 08:26 | 4 | 3.98 | 76904 | Type 2 | No | 690.57 | 28.77 | Yes | Standard | 12.5036 | 6150 | Yes
S-207-D | S-207 | D | 772531 | 09/22/2026 | 08:32 | 4.04 | 4.04 | 78444 | Type 4 | No | 690.67 | 28.78 | Yes | Standard | 12.819 | 6120 | Yes
S-208-A | S-208 | A | 772809 | 09/02/2026 | 13:19 | 4.03 | 4.01 | 58765 | Type 1 | No | 170.63 | 7.11 | No | Standard | 12.6923 | 4630 | No
S-208-B | S-208 | B | 772809 | 09/23/2026 | 10:34 | 3.98 | 4 | 79892 | Type 2 | No | 671.88 | 28 | Yes | Standard | 12.5036 | 6390 | Yes
S-208-C | S-208 | C | 772809 | 09/23/2026 | 10:42 | 4.03 | 4.01 | 80356 | Type 2 | No | 672.02 | 28 | Yes | Standard | 12.6923 | 6330 | Yes
S-208-D | S-208 | D | 772809 | 09/23/2026 | 10:48 | 3.97 | 3.97 | 77996 | Type 2 | No | 672.12 | 28.01 | Yes | Standard | 12.3786 | 6300 | Yes
S-209-A | S-209 | A | 772934 | 09/03/2026 | 10:19 | 4.01 | 4.01 | 53665 | Type 1 | No | 170.08 | 7.09 | No | Standard | 12.6293 | 4250 | No
S-209-B | S-209 | B | 772934 | 09/24/2026 | 10:58 | 4.03 | 4.01 | 78179 | Type 4 | No | 674.73 | 28.11 | Yes | Standard | 12.6923 | 6160 | Yes
S-209-C | S-209 | C | 772934 | 09/24/2026 | 11:05 | 3.97 | 4.01 | 76388 | Type 2 | No | 674.85 | 28.12 | Yes | Standard | 12.5036 | 6110 | Yes
S-209-D | S-209 | D | 772934 | 09/24/2026 | 11:14 | 4.02 | 4.04 | 77671 | Type 2 | No | 675 | 28.13 | Yes | Standard | 12.7556 | 6090 | Yes
S-210-A | S-210 | A | 773248 | 09/08/2026 | 09:47 | 6.01 | 5.99 | 84525 | Type 1 | No | 194.83 | 8.12 | No | Standard | 28.2743 | 2990 | No
S-210-B | S-210 | B | 773248 | 09/28/2026 | 09:07 | 6 | 6.02 | 122865 | Type 2 | No | 674.17 | 28.09 | Yes | Standard | 28.3687 | 4330 | Yes
S-210-C | S-210 | C | 773248 | 09/28/2026 | 09:15 | 5.99 | 6.01 | 115105 | Type 2 | No | 674.3 | 28.1 | Yes | Standard | 28.2743 | 4070 | Yes
S-211-A | S-211 | A | 773471 | 09/09/2026 | 08:52 | 4.02 | 3.98 | 55676 | Type 2 | No | 167.55 | 6.98 | No | Standard | 12.5664 | 4430 | No
S-211-B | S-211 | B | 773471 | 09/30/2026 | 11:21 | 4.03 | 4.03 | 77805 | Type 2 | No | 674.03 | 28.08 | Yes | Standard | 12.7556 | 6100 | Yes
S-211-C | S-211 | C | 773471 | 09/30/2026 | 11:27 | 3.98 | 3.98 | 75389 | Type 2 | No | 674.13 | 28.09 | Yes | Standard | 12.441 | 6060 | Yes
S-211-D | S-211 | D | 773471 | 09/30/2026 | 11:35 | 4.02 | 4.02 | 76419 | Type 3 | No | 674.27 | 28.09 | Yes | Standard | 12.6923 | 6020 | Yes
S-212-A | S-212 | A | 773586 | 09/10/2026 | 09:09 | 4 | 4 | 49128 | Type 3 | No | 169.03 | 7.04 | No | Standard | 12.5664 | 3910 | No
S-212-B | S-212 | B | 773586 | 10/01/2026 | 10:13 | 4 | 4 | 71883 | Type 1 | No | 674.1 | 28.09 | Yes | Standard | 12.5664 | 5720 | Yes
S-212-C | S-212 | C | 773586 | 10/01/2026 | 10:19 | 4.01 | 4.01 | 67937 | Type 1 | No | 674.2 | 28.09 | Yes | Standard | 12.6293 | 5380 | Yes
S-212-D | S-212 | D | 773586 | 10/01/2026 | 10:25 | 4 | 4.02 | 64400 | Type 2 | No | 674.3 | 28.1 | Yes | Standard | 12.6293 | 5100 | Yes
S-213-A | S-213 | A | 774119 | 09/17/2026 | 13:05 | 3.99 | 4.01 | 57566 | Type 2 | No | 168.22 | 7.01 | No | Standard | 12.5664 | 4580 | No
S-213-B | S-213 | B | 774119 | 10/08/2026 | 13:46 | 4 | 4 | 78777 | Type 2 | No | 672.9 | 28.04 | Yes | Standard | 12.5664 | 6270 | Yes
S-213-C | S-213 | C | 774119 | 10/08/2026 | 13:52 | 4 | 4 | 78413 | Type 2 | No | 673 | 28.04 | Yes | Standard | 12.5664 | 6240 | Yes
S-213-D | S-213 | D | 774119 | 10/08/2026 | 13:58 | 4.01 | 4.01 | 78045 | Type 1 | No | 673.1 | 28.05 | Yes | Standard | 12.6293 | 6180 | Yes
Cylinders on the break record |  |  | 110
Cylinders entering a strength test |  |  | 60

## Tests
Samples and strength tests, one line per delivery ticket, in the order the samples were molded
TICKET_NO | SETS | PLACEMENT_ID | MIXTURE | DATE_CAST | TIME_MOLDED | CYL_SIZE | CYLINDERS_REQUIRED | CYLINDERS_ENTERING | STRENGTH_TEST_PSI | LOW_PSI | HIGH_PSI | RANGE_PCT | RANGE_LIMIT_PCT | RANGE_NOTE | CURING_CLASS | CURING_NOTE | ENGINEER_DIRECTION | USED_FOR_ACCEPTANCE | REASON_NOT_USED | RESULT_FOR_INFORMATION_PSI | FRESH_CONCRETE
770418 | S-101 | P-01 | M-4000 | 08/03/2026 | 07:23 | 6x12 | 2 | 2 | 4250 | 4110 | 4390 | 6.59 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
770653 | S-102 | P-02 | M-4000 | 08/05/2026 | 08:12 | 6x12 | 2 | 2 | 4430 | 4390 | 4470 | 1.81 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
770812 | S-201 | P-04 | M-6000 | 08/06/2026 | 09:36 | 4x8 | 3 | 3 | 5920 | 5900 | 5960 | 1.01 | 10.6 |  | Standard |  |  | Yes |  |  | Within 2.4
771106 | S-103 | P-05 | M-4000 | 08/10/2026 | 06:52 | 6x12 | 2 | 0 |  |  |  |  | 6.6 |  | Standard |  |  | No | Tested outside the 20 hour tolerance of 3.10.3 | 4120 | Within 2.4
771131 | S-104 | P-05 | M-4000 | 08/10/2026 | 10:18 | 6x12 | 2 | 0 |  |  |  |  | 6.6 |  | Standard |  |  | No | Tested outside the 20 hour tolerance of 3.10.3 | 4060 | Within 2.4
771163 | S-202 | P-05 | M-4000 | 08/10/2026 | 14:37 | 6x12 | 2 | 2 | 3460 | 3420 | 3500 | 2.31 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
771342 | S-105 | P-06 | M-4000 | 08/12/2026 | 07:38 | 6x12 | 2 | 2 | 3480 | 3340 | 3620 | 8.05 | 6.6 | Range exceeds 3.10.4, counted | Standard |  |  | Yes |  |  | Outside 2.4
771469 | S-203 | P-07 | M-6000 | 08/13/2026 | 09:04 | 4x8 | 3 | 3 | 6250 | 6210 | 6300 | 1.44 | 10.6 |  | Standard |  |  | Yes |  |  | Within 2.4
771587 | S-106 | P-08 | M-4000 | 08/14/2026 | 07:17 | 6x12 | 2 | 2 | 4180 | 4130 | 4230 | 2.39 | 6.6 |  | Standard | Initial curing period over 48 hours |  | Yes |  |  | Outside 2.4
771604 | S-107 | P-08 | M-4000 | 08/14/2026 | 09:48 | 6x12 | 2 | 0 |  |  |  |  | 6.6 |  | Field |  |  | No | Field cured, not a strength test under 3.10.6 | 3390 | Within 2.4
771688 | S-108 | P-09 | M-4000 | 08/15/2026 | 06:43 | 6x12 | 2 | 2 | 4340 | 4300 | 4380 | 1.84 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
771842 | S-109 | P-10 | M-4000 | 08/17/2026 | 08:06 | 6x12 | 2 | 2 | 4220 | 4180 | 4260 | 1.9 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
771955 | S-204 | P-11 | M-6000 | 08/18/2026 | 09:53 | 4x8 | 3 | 3 | 6080 | 6030 | 6120 | 1.48 | 10.6 |  | Standard |  |  | Yes |  |  | Within 2.4
772071 | S-110 S-205 | P-12 | M-4000 | 08/19/2026 | 08:21 | 6x12 | 2 | 4 | 3500 | 3450 | 3550 | 2.86 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
772203 | S-206 | P-13 | M-6000 | 08/20/2026 | 09:26 | 4x8 | 3 | 3 | 5590 | 5560 | 5610 | 0.89 | 10.6 |  | Standard |  |  | Yes |  |  | Within 2.4
772316 | S-111 | P-14 | M-4000 | 08/21/2026 | 09:13 | 4x8 | 3 | 2 | 4240 | 4220 | 4260 | 0.94 | 10.6 |  | Standard |  |  | No | Incomplete test under 3.10.2 | 4240 | Within 2.4
772569 | S-112 | P-15 | M-4000 | 08/24/2026 | 13:44 | 6x12 | 2 | 2 | 4290 | 4250 | 4330 | 1.86 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
772531 | S-207 | P-16 | M-6000 | 08/24/2026 | 13:52 | 4x8 | 3 | 3 | 6150 | 6120 | 6180 | 0.98 | 10.6 |  | Standard |  |  | Yes |  |  | Within 2.4
772784 | S-113 | P-17 | M-4000 | 08/26/2026 | 07:19 | 6x12 | 2 | 2 | 4390 | 4350 | 4430 | 1.82 | 6.6 |  | Standard | Initial curing temperature outside 60 to 80 F | Set aside, letter of October 2, 2026 | No | Set aside by the engineer of record under 3.10.7 | 4390 | Within 2.4
772809 | S-208 | P-18 | M-6000 | 08/26/2026 | 10:41 | 4x8 | 3 | 3 | 6340 | 6300 | 6390 | 1.42 | 10.6 |  | Standard | Initial curing temperature outside 60 to 80 F |  | Yes |  |  | Within 2.4
772934 | S-209 | P-19 | M-6000 | 08/27/2026 | 08:14 | 4x8 | 3 | 3 | 6120 | 6090 | 6160 | 1.14 | 10.6 |  | Standard |  |  | Yes |  |  | Within 2.4
773127 | S-114 | P-20 | M-4000 | 08/29/2026 | 11:32 | 6x12 | 2 | 0 |  |  |  |  | 6.6 |  | Standard |  |  | No | Tested outside the 20 hour tolerance of 3.10.3 | 4300 | Within 2.4
773248 | S-210 | P-21 | M-4000 | 08/31/2026 | 06:57 | 6x12 | 2 | 2 | 4200 | 4070 | 4330 | 6.19 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
773295 | S-115 | P-21 | M-4000 | 08/31/2026 | 11:22 | 6x12 | 2 | 2 | 4300 | 4260 | 4340 | 1.86 | 6.6 |  | Standard |  |  | Yes |  |  | Within 2.4
773471 | S-211 | P-22 | M-6000 | 09/02/2026 | 09:19 | 4x8 | 3 | 3 | 6060 | 6020 | 6100 | 1.32 | 10.6 |  | Standard |  |  | Yes |  |  | Outside 2.4
773586 | S-212 | P-23 | M-6000 | 09/03/2026 | 08:07 | 4x8 | 3 | 3 | 5400 | 5100 | 5720 | 11.48 | 10.6 | Range exceeds 3.10.4, counted | Standard |  |  | Yes |  |  | Within 2.4
773902 | S-116 | P-24 | M-4000 | 09/08/2026 | 08:31 | 6x12 | 2 | 2 | 4310 | 4270 | 4350 | 1.86 | 6.6 |  | Standard | Initial curing temperature outside 60 to 80 F |  | Yes |  |  | Within 2.4
774119 | S-213 | P-26 | M-6000 | 09/10/2026 | 12:52 | 4x8 | 3 | 3 | 6230 | 6180 | 6270 | 1.44 | 10.6 |  | Standard |  |  | Yes |  |  | Within 2.4
Samples taken, one per delivery ticket |  |  | 28
Tests with a within-test range note |  |  | 2
Tests used that carry a curing note |  |  | 3
Samples outside a fresh concrete limit |  |  | 3

## Acceptance decks
M-4000, elevated decks, ramp slabs, stair landings and curbs: strength tests in the order their samples were molded
TICKET_NO | SETS | PLACEMENT_ID | DATE_CAST | TIME_MOLDED | STRENGTH_TEST_PSI | MOVING_AVERAGE_3 | CRITERION_A | CRITERION_B | NOTES | USED_ORDINAL | B_ORDINAL
July | S-094 |  | 07/28/2026 |  | 4310 |  |  |  | Carried from the July summary | 1
July | S-095 |  | 07/30/2026 |  | 4150 |  |  |  | Carried from the July summary | 2
770418 | S-101 | P-01 | 08/03/2026 | 07:23 | 4250 | 4236.7 | Meets | Meets |  | 3
770653 | S-102 | P-02 | 08/05/2026 | 08:12 | 4430 | 4276.7 | Meets | Meets |  | 4
771106 | S-103 | P-05 | 08/10/2026 | 06:52 |  |  |  |  | Not used: Tested outside the 20 hour tolerance of 3.10.3
771131 | S-104 | P-05 | 08/10/2026 | 10:18 |  |  |  |  | Not used: Tested outside the 20 hour tolerance of 3.10.3
771163 | S-202 | P-05 | 08/10/2026 | 14:37 | 3460 | 4046.7 | Meets | Fails |  | 5 | 1
771342 | S-105 | P-06 | 08/12/2026 | 07:38 | 3480 | 3790 | Below f'c | Fails | Range exceeds 3.10.4, counted | 6 | 2
771587 | S-106 | P-08 | 08/14/2026 | 07:17 | 4180 | 3706.7 | Below f'c | Meets | Initial curing period over 48 hours | 7
771604 | S-107 | P-08 | 08/14/2026 | 09:48 |  |  |  |  | Not used: Field cured, not a strength test under 3.10.6
771688 | S-108 | P-09 | 08/15/2026 | 06:43 | 4340 | 4000 | Meets | Meets |  | 8
771842 | S-109 | P-10 | 08/17/2026 | 08:06 | 4220 | 4246.7 | Meets | Meets |  | 9
772071 | S-110 S-205 | P-12 | 08/19/2026 | 08:21 | 3500 | 4020 | Meets | Meets |  | 10
772316 | S-111 | P-14 | 08/21/2026 | 09:13 |  |  |  |  | Not used: Incomplete test under 3.10.2
772569 | S-112 | P-15 | 08/24/2026 | 13:44 | 4290 | 4003.3 | Meets | Meets |  | 11
772784 | S-113 | P-17 | 08/26/2026 | 07:19 |  |  |  |  | Not used: Set aside by the engineer of record under 3.10.7
773127 | S-114 | P-20 | 08/29/2026 | 11:32 |  |  |  |  | Not used: Tested outside the 20 hour tolerance of 3.10.3
773248 | S-210 | P-21 | 08/31/2026 | 06:57 | 4200 | 3996.7 | Below f'c | Meets |  | 12
773295 | S-115 | P-21 | 08/31/2026 | 11:22 | 4300 | 4263.3 | Meets | Meets |  | 13
773902 | S-116 | P-24 | 09/08/2026 | 08:31 | 4310 | 4270 | Meets | Meets | Initial curing temperature outside 60 to 80 F | 14
Strength tests used for acceptance | 12
Lowest strength test (psi) | 3460
Moving averages of three below f'c, criterion (a) | 3
Lowest moving average of three (psi) | 3706.7
Tests below f'c by more than the allowance, criterion (b) | 2
First placement with a test failing criterion (b) | P-05
Second placement with a test failing criterion (b) | P-06
Third placement with a test failing criterion (b)
Placements with a test failing criterion (b) | P-05 P-06
Acceptance under 3.11.1 | Does not meet 3.11.1

## Acceptance columns
M-6000, columns and shear walls: strength tests in the order their samples were molded
TICKET_NO | SETS | PLACEMENT_ID | DATE_CAST | TIME_MOLDED | STRENGTH_TEST_PSI | MOVING_AVERAGE_3 | CRITERION_A | CRITERION_B | NOTES | USED_ORDINAL | B_ORDINAL
July | S-190 |  | 07/22/2026 |  | 6190 |  |  |  | Carried from the July summary | 1
July | S-192 |  | 07/29/2026 |  | 5870 |  |  |  | Carried from the July summary, as corrected September 15 | 2
770812 | S-201 | P-04 | 08/06/2026 | 09:36 | 5920 | 5993.3 | Below f'c | Meets |  | 3
771469 | S-203 | P-07 | 08/13/2026 | 09:04 | 6250 | 6013.3 | Meets | Meets |  | 4
771955 | S-204 | P-11 | 08/18/2026 | 09:53 | 6080 | 6083.3 | Meets | Meets |  | 5
772203 | S-206 | P-13 | 08/20/2026 | 09:26 | 5590 | 5973.3 | Below f'c | Meets |  | 6
772531 | S-207 | P-16 | 08/24/2026 | 13:52 | 6150 | 5940 | Below f'c | Meets |  | 7
772809 | S-208 | P-18 | 08/26/2026 | 10:41 | 6340 | 6026.7 | Meets | Meets | Initial curing temperature outside 60 to 80 F | 8
772934 | S-209 | P-19 | 08/27/2026 | 08:14 | 6120 | 6203.3 | Meets | Meets |  | 9
773471 | S-211 | P-22 | 09/02/2026 | 09:19 | 6060 | 6173.3 | Meets | Meets |  | 10
773586 | S-212 | P-23 | 09/03/2026 | 08:07 | 5400 | 5860 | Below f'c | Meets | Range exceeds 3.10.4, counted | 11
774119 | S-213 | P-26 | 09/10/2026 | 12:52 | 6230 | 5896.7 | Below f'c | Meets |  | 12
Strength tests used for acceptance | 10
Lowest strength test (psi) | 5400
Moving averages of three below f'c, criterion (a) | 5
Lowest moving average of three (psi) | 5860
Tests below f'c by more than the allowance, criterion (b) | 0
First placement with a test failing criterion (b)
Second placement with a test failing criterion (b)
Third placement with a test failing criterion (b)
Placements with a test failing criterion (b) | None
Acceptance under 3.11.1 | Does not meet 3.11.1

## Sampling
Sampling check under 3.10.1, one line per mixture per day of placement
DATE | MIXTURE | PLACEMENTS | CUBIC_YARDS | SURFACE_AREA_SF | BY_VOLUME | BY_AREA | TESTS_REQUIRED | SAMPLES_TAKEN | TESTS_USED | STATUS | WHAT_THE_RECORDS_SHOW | SHORT_DAY | SHORT_DAYS_SO_FAR
08/03/2026 | M-4000 | P-01 | 104 | 4810 | 1 | 1 | 1 | 1 | 1 | Met
08/05/2026 | M-4000 | P-02 P-03 | 107 | 4950 | 1 | 1 | 1 | 1 | 1 | Met | No cylinders from P-03; the day's total is covered by the test from P-02
08/06/2026 | M-6000 | P-04 | 38 | 0 | 1 | 0 | 1 | 1 | 1 | Met
08/10/2026 | M-4000 | P-05 | 318 | 14720 | 3 | 3 | 3 | 3 | 1 | Short | 3 samples taken, 1 test used of 3 required; S-103 outside the age tolerance; S-104 outside the age tolerance | 08/10 M-4000 | 08/10 M-4000
08/12/2026 | M-4000 | P-06 | 101 | 4670 | 1 | 1 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000
08/13/2026 | M-6000 | P-07 | 41 | 0 | 1 | 0 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000
08/14/2026 | M-4000 | P-08 | 112 | 5180 | 1 | 2 | 2 | 2 | 1 | Short | 2 samples taken, 1 test used of 2 required; S-107 field cured | 08/14 M-4000 | 08/10 M-4000; 08/14 M-4000
08/15/2026 | M-4000 | P-09 | 150 | 4860 | 1 | 1 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000
08/17/2026 | M-4000 | P-10 | 151 | 6990 | 2 | 2 | 2 | 1 | 1 | Short | 1 sample taken, 1 test used of 2 required | 08/17 M-4000 | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000
08/18/2026 | M-6000 | P-11 | 36 | 0 | 1 | 0 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000
08/19/2026 | M-4000 | P-12 | 106 | 4905 | 1 | 1 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000
08/20/2026 | M-6000 | P-13 | 37 | 0 | 1 | 0 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000
08/21/2026 | M-4000 | P-14 | 96 | 3110 | 1 | 1 | 1 | 1 | 0 | Short | 1 sample taken, 0 tests used of 1 required; S-111 incomplete test | 08/21 M-4000 | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000
08/24/2026 | M-4000 | P-15 | 103 | 4770 | 1 | 1 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000
08/24/2026 | M-6000 | P-16 | 39 | 0 | 1 | 0 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000
08/26/2026 | M-4000 | P-17 | 99 | 4580 | 1 | 1 | 1 | 1 | 0 | Short | 1 sample taken, 0 tests used of 1 required; S-113 set aside by the engineer | 08/26 M-4000 | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000
08/26/2026 | M-6000 | P-18 | 40 | 0 | 1 | 0 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000
08/27/2026 | M-6000 | P-19 | 52 | 1390 | 1 | 1 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000
08/29/2026 | M-4000 | P-20 | 107 | 4950 | 1 | 1 | 1 | 1 | 0 | Short | 1 sample taken, 0 tests used of 1 required; S-114 outside the age tolerance | 08/29 M-4000 | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000
08/31/2026 | M-4000 | P-21 | 212 | 9810 | 2 | 2 | 2 | 2 | 2 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000
09/02/2026 | M-6000 | P-22 | 38 | 0 | 1 | 0 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000
09/03/2026 | M-6000 | P-23 | 49 | 1310 | 1 | 1 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000
09/08/2026 | M-4000 | P-24 | 88 | 2850 | 1 | 1 | 1 | 1 | 1 | Met |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000
09/10/2026 | M-6000 | P-25 P-26 | 86 | 1310 | 1 | 1 | 1 | 1 | 1 | Met | No cylinders from P-25; the day's total is covered by the test from P-26 |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000
09/11/2026 | M-4000 | P-27 | 14 | 640 | 1 | 1 | 1 | 0 | 0 | Short | No sample taken on the day | 09/11 M-4000 | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000; 09/11 M-4000
Mixture days of placement in the period |  |  | 25
Days on which a mixture was sampled short of 3.10.1 |  |  | 7
Days short, listed |  |  | 08/10 M-4000; 08/14 M-4000; 08/17 M-4000; 08/21 M-4000; 08/26 M-4000; 08/29 M-4000; 09/11 M-4000

## Note to Gunnar
Note to Gunnar Brekke on the project 2417 acceptance summary
Gunnar, this is the acceptance summary for the August and September placements on project 2417. Every cylinder strength is computed on the Cylinders tab from the load and the two measured diameters on the break record, and every figure on the first tab reads from the tabs behind it. Neither mixture meets 3.11.1 for the period. The records differ from your memo and from the correspondence in several places, and each is set out below.
M-4000 has 12 strength tests used for acceptance. Two fail criterion (b), where the allowance is 500 psi. Set S-202 from P-05, the Level 2 bays C and D deck cast August 10, tested at 3,460 psi. Set S-105 from P-06, the Level 3 bay A deck cast August 12, tested at 3,480 psi. Under 3.11.2 both placements go to the engineer of record, and the contractor investigates under ACI 318-19 section 26.12.6. For cores the floors are 3,400 psi on the average of three and 3,000 psi on a single core.
The moving average of three on M-4000 is below 4,000 psi three times: 3,790.0 psi at S-105, 3,706.7 psi at S-106 and 3,996.7 psi at S-210, the first of the two August 31 samples. The average at S-108 is 4,000.0 psi, which equals f'c and meets criterion (a). The first two averages take in the last two July tests used for acceptance, 4,310 and 4,150 psi.
M-6000 has 10 strength tests used for acceptance, and none fails criterion (b), where the allowance is 600 psi. The lowest test is 5,400 psi on S-212 from P-23, which is below f'c by exactly the allowance. The moving average is below 6,000 psi five times: 5,993.3 psi at S-201, 5,973.3 psi at S-206, 5,940.0 psi at S-207, 5,860.0 psi at S-212 and 5,896.7 psi at S-213. Under 3.11.2 the contractor takes steps to increase the average, and no column or wall placement goes to cores.
The first two averages of each mixture take in the last two July tests used for acceptance. For M-6000 those are 6,190 psi on S-190 and 5,870 psi on S-192, the second as corrected by your letter of September 15. The July table still prints 5,960 psi for S-192. With the printed figure the average at S-201 would read 6,023.3 psi and meet criterion (a), so the correction decides that average.
The Level 3 grid 5 to 8 columns, P-13, do not fail. Cylinder C of set S-206 broke at 4,700 psi with a Type 5 fracture, and the break record says the cap lifted on one side. Under 3.10.5 that cylinder is discarded and reserve cylinder E, broken the same morning, enters the test. The test is 5,590 psi on cylinders B, D and E.
L. Brandvold's lines in the field sampling log are on the 12 hour clock. Set S-202 is written at 2:37 and set S-207 at 1:52, and the placement log puts both in the afternoon, at 14:37 and 13:52. Read that way both sets were broken inside the age tolerance, at 28.77 and 28.77 days. S-202 is the test that fails on P-05. The line for S-114 is dated 08/28/2026, but the placement log has Level 4 bay C on 08/29/2026, a Saturday, as your memo does.
The age tolerance cost us three sets, which your memo did not expect. Reckoned in hours from the time of molding, S-103 and S-104 from the Labor Day group were broken at 29.07 and 28.94 days, and S-114 from the Saturday placement at 26.91 days. Each is more than 20 hours from 28 days. S-202, S-112, S-207 and S-108 were broken on the same days and are inside the tolerance.
The contractor's note of September 10 asks that the Level 3 bay A set, S-105, be voided. The break record shows no defect on either cylinder, and the engineer's letter of October 2 gives no direction on that result, so the test stands at 3,480 psi. Its within-test range is 8.05 percent against the 6.6 percent of 3.10.4, and the field report shows water added before the sample and a slump of 5.25 inches. The contractor's statement that the deck mixture has no test under the line is not borne out.
Set S-113 from P-17 is set aside under 3.10.7 on the engineer's letter of October 2, and its 4,390 psi is reported for information. Your memo says no other set has a curing excursion, and the field sampling log shows three. S-208 was in box 2 on the same day, and its thermometer reads 91 F, written high first. S-116 reads 57 F. S-106 stayed in the box 74.4 hours. All three are counted under 3.10.6 with the excursion noted.
Sets S-110 and S-205 are one sample. Both lines show truck 33 batched at 07:33 with the same slump, air and temperature, and the ticket on the S-205 line, 772017, is 772071 with two digits turned. The test is 3,500 psi on four cylinders, which is below f'c by exactly 500 psi and meets criterion (b). Set S-107 was left on the deck for the contractor and is field cured, and its 28 day cylinders averaged 3,390 psi. Set S-111 lost cylinder D to a spalled edge after its reserve had gone at 7 days, so it is an incomplete test.
Sampling fell short of 3.10.1 on 7 mixture days, all of them on M-4000 and listed on the first tab. On August 10 three samples were taken from the 318 cubic yard placement and three tests were required, but only S-202 gave a test used for acceptance. The owner's representative should be told that the day was short. August 14 needed two tests for 5,180 square feet and has one. August 17 needed two for 151 cubic yards and has one. August 21, 26 and 29 each lost their only test.
Your memo carries September 10 and September 11 as sampled short, and the records bear out only the second. The curbs, P-27, were the only M-4000 placed on September 11, and no sample was taken that day. No cylinders were made from the stair 1 shear walls, P-25, on September 10, but the day's M-6000 was 86 cubic yards across P-25 and P-26. One test was required, and S-213 from P-26 provides it. The same holds for the stair landings, P-03, on August 5.
For the owner's representative's second question, 3 samples were outside a limit of 2.4: S-105 at a slump of 5.25 inches, S-106 at 7.8 percent air and S-211 at 4.2 percent air. They are noted under 3.12.2 and do not change the acceptance. For the transmittal, please raise the two criterion (b) placements with the engineer, ask the contractor what it is changing on both mixtures to lift the averages, and tell the contractor in writing that S-105 stays in the record.