## Prelim Log
Preliminary notices received, Larkspur Crossing Building B, job file 2210-B
Entered by the owner from each notice as received. DATE_MAILED is the date on the claimant's proof of service or the postmark; RECEIVED is the date the notice reached our office.
NOTICE_FROM | TRADE_OR_MATERIAL | CONTRACTED_WITH | DATE_ON_NOTICE | DATE_MAILED | RECEIVED | FIRST_FURNISHED_PER_NOTICE | ESTIMATED_VALUE
Ostrowski Electric, Inc. | Electrical | Dunmore-Kettle Builders, Inc. | 01/28/2026 | 01/30/2026 | 02/03/2026 | 01/19/2026 | 685000
Tallac Concrete, Inc. | Site concrete | Dunmore-Kettle Builders, Inc. | 02/06/2026 | 02/09/2026 | 02/11/2026 | 02/02/2026 | 412000
Foothill Ready Mix, Inc. | Ready mixed concrete | Tallac Concrete, Inc. | 02/10/2026 | 02/11/2026 | 02/13/2026 | 02/05/2026 | 96000
Petrakis Plumbing, Inc. | Plumbing | Dunmore-Kettle Builders, Inc. | 02/10/2026 | 02/12/2026 | 02/17/2026 | 02/09/2026 | 271300
Capitol Wire & Lighting, Inc. | Switchgear, wire, fixtures | Ostrowski Electric, Inc. | 02/13/2026 | 02/16/2026 | 02/18/2026 | 02/04/2026 | 141500
R. Nakamura Framing, Inc. | Rough carpentry | Dunmore-Kettle Builders, Inc. | 02/27/2026 | 03/02/2026 | 03/04/2026 | 02/23/2026 | 512400
Auburn Scaffold & Shoring, Inc. | Scaffold and shoring rental | R. Nakamura Framing, Inc. | 03/03/2026 | 03/05/2026 | 03/09/2026 | 02/27/2026 | 36000
Lindqvist Fire Protection | Fire sprinklers | Dunmore-Kettle Builders, Inc. | 03/06/2026 | 03/09/2026 | 03/11/2026 | 03/02/2026 | 142650
Fenwick Roofing, Inc. | Roofing | Dunmore-Kettle Builders, Inc. | 03/11/2026 | 03/12/2026 | 03/16/2026 | 03/09/2026 | 298750
Sierra Pipe & Supply, Inc. | Pipe, fittings, fixtures | Petrakis Plumbing, Inc. | 03/13/2026 | 03/16/2026 | 03/18/2026 | 03/03/2026 | 84500
Kastner Mechanical Contractors, Inc. | HVAC | Dunmore-Kettle Builders, Inc. | 03/18/2026 | 03/20/2026 | 03/24/2026 | 03/16/2026 | 444600
Calder Drywall & Plaster, LLC | Drywall and plaster | Dunmore-Kettle Builders, Inc. | 04/22/2026 | 04/24/2026 | 04/28/2026 | 04/20/2026 | 194300
Calder Bros. Masonry, Inc. | Masonry veneer, trash enclosure | Dunmore-Kettle Builders, Inc. | 04/27/2026 | 04/29/2026 | 05/01/2026 | 04/22/2026 | 58600
Abrego Glass & Glazing | Storefront and glazing | Dunmore-Kettle Builders, Inc. | 05/01/2026 | 05/04/2026 | 05/06/2026 | 04/27/2026 | 186900
Bautista Painting Co. | Painting | Dunmore-Kettle Builders, Inc. | 05/22/2026 | 05/27/2026 | 05/29/2026 | 05/18/2026 | 76900
Hedrick & Sons Building Supply | Lumber, trusses, sheathing | R. Nakamura Framing, Inc. | 05/27/2026 | 05/29/2026 | 06/02/2026 | 05/11/2026 | 68500

## Waiver Log
Waivers and releases received with payment applications, Larkspur Crossing Building B
FORM_TITLE is the title printed on the document received; PAY_APP is the payment application the document came in with. CHECK_REF is the check the form names, where the form names one. EXCEPTIONS is what the form lists as excepted. The log continues in the right-hand block, columns J to R.
CLAIMANT | PAY_APP | FORM_TITLE | THROUGH_DATE | AMOUNT | EXCEPTIONS | CHECK_REF | DATE_SIGNED | RECEIVED | CLAIMANT_2 | PAY_APP_2 | FORM_TITLE_2 | THROUGH_DATE_2 | AMOUNT_2 | EXCEPTIONS_2 | CHECK_REF_2 | DATE_SIGNED_2 | RECEIVED_2
Abrego Glass & Glazing | 6 | Unconditional Waiver and Release on Progress Payment | 05/31/2026 | 112765 | None |  | 07/01/2026 | 07/06/2026 | Ostrowski Electric, Inc. | 3 | Unconditional Waiver and Release on Progress Payment | 02/28/2026 | 152950 | None |  | 03/31/2026 | 04/03/2026
Abrego Glass & Glazing | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 64790 | None |  | 08/03/2026 | 08/03/2026 | Ostrowski Electric, Inc. | 4 | Unconditional Waiver and Release on Progress Payment | 03/31/2026 | 121600 | None |  | 05/01/2026 | 05/05/2026
Bautista Painting Co. | 6 | Unconditional Waiver and Release on Progress Payment | 05/31/2026 | 12825 | None |  | 07/02/2026 | 07/06/2026 | Ostrowski Electric, Inc. | 5 | Unconditional Waiver and Release on Progress Payment | 04/30/2026 | 98325 | None |  | 06/01/2026 | 06/03/2026
Bautista Painting Co. | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 21755 | None |  | 08/03/2026 | 08/03/2026 | Ostrowski Electric, Inc. | 6 | Unconditional Waiver and Release on Progress Payment | 05/31/2026 | 89305 | None |  | 06/30/2026 | 07/06/2026
Bautista Painting Co. | 8 | Unconditional Waiver and Release on Progress Payment | 07/31/2026 | 38475 | None |  | 08/03/2026 | 08/26/2026 | Ostrowski Electric, Inc. | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 120113 | None |  | 07/31/2026 | 08/03/2026
Calder Bros. Masonry, Inc. | 6 | Unconditional Waiver and Release on Progress Payment | 05/31/2026 | 31350 | None |  | 07/02/2026 | 07/06/2026 | Ostrowski Electric, Inc. | 8 | Conditional Waiver and Release on Progress Payment | 07/31/2026 | 41230 | None | Dunmore-Kettle Builders check 4461 | 08/19/2026 | 08/26/2026
Calder Drywall & Plaster, LLC | 5 | Unconditional Waiver and Release on Progress Payment | 04/30/2026 | 8700 | None |  | 06/02/2026 | 06/03/2026 | Ostrowski Electric, Inc. |  | Conditional Waiver and Release on Progress Payment | 08/11/2026 | 27227 | None | Dunmore-Kettle Builders check 4479 | 09/30/2026 | 10/01/2026
Calder Drywall & Plaster, LLC | 6 | Unconditional Waiver and Release on Progress Payment | 05/31/2026 | 46170 | None |  | 07/01/2026 | 07/06/2026 | Petrakis Plumbing, Inc. | 3 | Unconditional Waiver and Release on Progress Payment | 02/28/2026 | 61370 | None |  | 03/31/2026 | 04/03/2026
Calder Drywall & Plaster, LLC | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 100515 | None |  | 07/31/2026 | 08/03/2026 | Petrakis Plumbing, Inc. | 4 | Unconditional Waiver and Release on Progress Payment | 03/31/2026 | 48830 | None |  | 05/01/2026 | 05/05/2026
Calder Drywall & Plaster, LLC | 8 | Subcontractor's Release and Affidavit, Dunmore-Kettle form S-9 | 07/31/2026 | 29200 | None stated |  | 08/03/2026 | 08/26/2026 | Petrakis Plumbing, Inc. | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 116525 | None |  | 07/30/2026 | 08/03/2026
Fenwick Roofing, Inc. | 4 | Unconditional Waiver and Release on Progress Payment | 03/31/2026 | 95410 | None |  | 05/04/2026 | 05/05/2026 | Petrakis Plumbing, Inc. | 8 | Unconditional Waiver and Release on Progress Payment | 07/31/2026 | 37166 | None |  | 08/24/2026 | 08/27/2026
Fenwick Roofing, Inc. | 5 | Unconditional Waiver and Release on Progress Payment | 04/30/2026 | 173465 | None |  | 06/01/2026 | 06/03/2026 | R. Nakamura Framing, Inc. | 4 | Unconditional Waiver and Release on Progress Payment | 03/31/2026 | 164730 | None |  | 05/04/2026 | 05/05/2026
Fenwick Roofing, Inc. | 7 | Conditional Waiver and Release on Final Payment |  | 14937.5 | Disputed claims for extras: $0.00 | Dunmore-Kettle Builders check 4448 | 07/29/2026 | 08/03/2026 | R. Nakamura Framing, Inc. | 5 | Unconditional Waiver and Release on Progress Payment | 04/30/2026 | 194370 | None |  | 06/01/2026 | 06/03/2026
Kastner Mechanical Contractors, Inc. | 4 | Unconditional Waiver and Release on Progress Payment | 03/31/2026 | 32110 | None |  | 05/01/2026 | 05/05/2026 | R. Nakamura Framing, Inc. | 6 | Unconditional Waiver and Release on Progress Payment | 05/31/2026 | 106400 | None |  | 06/30/2026 | 07/06/2026
Kastner Mechanical Contractors, Inc. | 5 | Unconditional Waiver and Release on Progress Payment | 04/30/2026 | 97565 | None |  | 06/01/2026 | 06/03/2026 | R. Nakamura Framing, Inc. | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 21280 | None |  | 07/31/2026 | 08/03/2026
Kastner Mechanical Contractors, Inc. | 6 | Unconditional Waiver and Release on Progress Payment | 05/31/2026 | 66860 | None |  | 06/30/2026 | 07/06/2026 | Tallac Concrete, Inc. | 3 | Unconditional Waiver and Release on Progress Payment | 02/28/2026 | 71250 | None |  | 03/30/2026 | 04/03/2026
Kastner Mechanical Contractors, Inc. | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 88920 | None |  | 07/31/2026 | 08/03/2026 | Tallac Concrete, Inc. | 4 | Unconditional Waiver and Release on Progress Payment | 03/31/2026 | 158650 | None |  | 05/01/2026 | 05/05/2026
Kastner Mechanical Contractors, Inc. | 8 | Conditional Waiver and Release on Progress Payment | 07/31/2026 | 73910 | None | Dunmore-Kettle Builders check 4460 | 08/18/2026 | 08/26/2026 | Tallac Concrete, Inc. | 5 | Unconditional Waiver and Release on Progress Payment | 04/30/2026 | 143710 | None |  | 06/01/2026 | 06/03/2026
Lindqvist Fire Protection | 5 | Unconditional Waiver and Release on Progress Payment | 04/30/2026 | 69501.5 | None |  | 06/02/2026 | 06/03/2026 | Tallac Concrete, Inc. | 6 | Lien release letter on Tallac Concrete letterhead | 05/08/2026 | 12675 | Letter says all claims for the May billing and retention are released on payment of the balance |  | 05/29/2026 | 07/06/2026
Lindqvist Fire Protection | 7 | Unconditional Waiver and Release on Progress Payment | 06/30/2026 | 66016 | None |  | 08/03/2026 | 08/03/2026 | Capitol Wire & Lighting, Inc. | 8 | Conditional Waiver and Release on Final Payment |  | 8940 | Disputed claims for extras: $14,540.00 | Dunmore-Kettle Builders check 4488 | 10/08/2026 | 10/12/2026

## Owner Payments
Payments by the owner, Larkspur Crossing Building B. Dunmore-Kettle Builders, Inc., contract sum $3,748,250.00, approved change orders 1 to 6 $100,000.00, adjusted contract sum $3,848,250.00, retention 5 percent
PAY_APP | PERIOD_THROUGH | RECEIVED | AMOUNT_CERTIFIED | RETENTION_WITHHELD | AMOUNT_PAID | CHECK_NO | CHECK_DATE | CLEARED | STATUS
1 | 01/31/2026 | 02/04/2026 | 128640 | 6432 | 122208 | 10877 | 02/20/2026 | 02/25/2026 | Paid, cleared
2 | 02/28/2026 | 03/04/2026 | 333680 | 16684 | 316996 | 10880 | 03/20/2026 | 03/25/2026 | Paid, cleared
3 | 03/31/2026 | 04/03/2026 | 719435 | 35971.75 | 683463.25 | 10885 | 04/21/2026 | 04/24/2026 | Paid, cleared
4 | 04/30/2026 | 05/05/2026 | 901415 | 45070.75 | 856344.25 | 10889 | 05/21/2026 | 05/27/2026 | Paid, cleared
5 | 05/31/2026 | 06/03/2026 | 643750 | 32187.5 | 611562.5 | 10895 | 06/19/2026 | 06/24/2026 | Paid, cleared
6 | 06/30/2026 | 07/06/2026 | 656610 | 32830.5 | 623779.5 | 10898 | 07/22/2026 | 07/27/2026 | Paid, cleared
7 | 07/31/2026 | 08/03/2026 | 312390 | 15619.5 | 296770.5 | 10905 | 08/14/2026 | 08/18/2026 | Paid, cleared
8 | 08/11/2026 | 08/26/2026 | 152330 | 7616.5 | 0 |  |  |  | Held pending resolution of recorded claims
Retention release |  |  |  |  | 0 |  |  |  | Not paid; requested with application 8
Totals |  |  | 3848250 | 192412.5 | 3511124
Retention withheld to date on applications 1 through 8 is the figure the direct contractor asks to have released with application 8.
Agreements the owner signed itself for the same project, paid from the owner's account
VENDOR | SCOPE | AGREEMENT_DATE | AGREEMENT_AMOUNT | PAID_TO_DATE | LAST_PAYMENT | BALANCE | WAIVER_ON_FILE | STATUS
Wexford Land Surveying | Construction staking and ALTA survey | 01/08/2026 | 14900 | 14900 | 07/24/2026 | 0 | None requested | Paid in full
Placer Materials Testing | Special inspection and materials testing | 01/12/2026 | 27350 | 27350 | 08/21/2026 | 0 | None requested | Paid in full
Sorensen Landscape Co. | Landscape planting, irrigation, site furnishings | 05/19/2026 | 88400 | 63320 | 08/14/2026 | 25080 | Unconditional Waiver and Release on Progress Payment through 07/31/2026, signed 08/14/2026 | Final invoice held, plant replacement on the punch list

## Subcontractors
Subcontractor list submitted by Dunmore-Kettle Builders, Inc. with payment application 1, updated through application 7
SUBCONTRACTOR | TRADE | SUBCONTRACT_DATE | SUBCONTRACT_VALUE | CHANGE_ORDERS | RETENTION_RATE | SUPPLIERS_LISTED
Ostrowski Electric, Inc. | Electrical | 12/30/2025 | 685000 | 0 | 5% | Capitol Wire & Lighting, Inc.
Tallac Concrete, Inc. | Site concrete | 01/06/2026 | 412000 | 0 | 5% | Norcal Rebar & Mesh, LLC; Foothill Ready Mix, Inc.
Petrakis Plumbing, Inc. | Plumbing | 01/22/2026 | 271300 | 6480 | 5% | Sierra Pipe & Supply, Inc.
R. Nakamura Framing, Inc. | Rough carpentry | 02/11/2026 | 512400 | 0 | 5% | Hedrick & Sons Building Supply; Auburn Scaffold & Shoring
Lindqvist Fire Protection | Fire sprinklers | 02/18/2026 | 142650 | 0 | 5%
Kastner Mechanical Contractors, Inc. | HVAC | 02/20/2026 | 444600 | 0 | 5% | Pacific Comfort Products; Granite Bay Sheet Metal; Sierra Test and Balance (sub-tier)
Fenwick Roofing, Inc. | Roofing | 02/26/2026 | 298750 | 0 | 5%
Calder Drywall & Plaster, LLC | Drywall and plaster | 03/24/2026 | 194300 | 0 | 5%
Abrego Glass & Glazing | Storefront and glazing | 04/08/2026 | 186900 | 0 | 5%
Calder Bros. Masonry, Inc. | Masonry veneer, trash enclosure | 04/14/2026 | 58600 | 0 | 5%
Bautista Painting Co. | Painting | 04/30/2026 | 76900 | 4280 | 5%

## Certified Mail
Outgoing certified mail, job file 2210-B, Larkspur Crossing Building B
Kept by the construction manager. RETURN_RECEIPT is the date on the green card when it came back, blank where it has not.
DATE_MAILED | ARTICLE_NO | ADDRESSEE | CITY | CONTENTS | RETURN_RECEIPT
03/17/2026 | 7021 0950 0001 8842 1176 | City of Roseville, Building Division | Roseville | Revised sheet S-201 and engineer's letter, permit B25-1187 | 03/19/2026
05/14/2026 | 7021 0950 0001 8842 1244 | Dunmore-Kettle Builders | Rocklin | Owner's decision on change order request 6 | 05/15/2026
06/30/2026 | 7021 0950 0001 8842 1329 | Tallac Concrete Inc | Lincoln | Letter on claim of lien, Doc. No. 2026-0060418 | 07/02/2026
07/09/2026 | 7021 0950 0001 8842 1367 | Foothill Ready Mix | Loomis | Letter on claim of lien, Doc. No. 2026-0063905 | 07/13/2026
08/31/2026 | 7022 1670 0002 3391 4108 | Ostrowski Electric Inc | Sacramento | Copy of notice of completion, Doc. No. 2026-0081562 | 09/02/2026
08/31/2026 | 7022 1670 0002 3391 4122 | Tallac Concrete Inc | Lincoln | Copy of notice of completion, Doc. No. 2026-0081562 | 09/03/2026
08/31/2026 | 7022 1670 0002 3391 4153 | R Nakamura Framing | Newcastle | Copy of notice of completion, Doc. No. 2026-0081562 | 09/02/2026
08/31/2026 | 7022 1670 0002 3391 4160 | Lindqvist Fire Protection | Rancho Cordova | Copy of notice of completion, Doc. No. 2026-0081562 | 09/03/2026
08/31/2026 | 7022 1670 0002 3391 4191 | Fenwick Roofing Inc | Rocklin | Copy of notice of completion, Doc. No. 2026-0081562 | 09/01/2026
08/31/2026 | 7022 1670 0002 3391 4214 | Kastner Mechanical | Sacramento | Copy of notice of completion, Doc. No. 2026-0081562 | 09/02/2026
08/31/2026 | 7022 1670 0002 3391 4238 | Abrego Glass and Glazing | Sacramento | Copy of notice of completion, Doc. No. 2026-0081562 | 09/04/2026
08/31/2026 | 7022 1670 0002 3391 4252 | Calder Bros Masonry | Penryn | Copy of notice of completion, Doc. No. 2026-0081562 | 09/02/2026
08/31/2026 | 7022 1670 0002 3391 4283 | Foothill Ready Mix | Loomis | Copy of notice of completion, Doc. No. 2026-0081562 | 09/01/2026
08/31/2026 | 7022 1670 0002 3391 4290 | Auburn Scaffold and Shoring | Auburn | Copy of notice of completion, Doc. No. 2026-0081562 | 09/02/2026
09/08/2026 | 7022 1670 0002 3391 4337 | Petrakis Plumbing | Roseville | Copy of notice of completion, Doc. No. 2026-0081562 | 09/09/2026
09/08/2026 | 7022 1670 0002 3391 4351 | Bautista Painting | Roseville | Copy of notice of completion, Doc. No. 2026-0081562 | 09/10/2026
09/08/2026 | 7022 1670 0002 3391 4375 | Hedrick and Sons Bldg Supply | Auburn | Copy of notice of completion, Doc. No. 2026-0081562 | 09/11/2026
09/08/2026 | 7022 1670 0002 3391 4382 | Sierra Test and Balance | Rancho Cordova | Copy of notice of completion, Doc. No. 2026-0081562 | 09/10/2026
09/08/2026 | 7022 1670 0002 3391 4399 | Sierra Pipe and Supply | Rancho Cordova | Copy of notice of completion, Doc. No. 2026-0081562
09/09/2026 | 7022 1670 0002 3391 4629 | Dunmore-Kettle Builders | Rocklin | Copy of notice of completion, Doc. No. 2026-0081562 | 09/10/2026
09/09/2026 | 7022 1670 0002 3391 4643 | Capitol Wire and Lighting | Sacramento | Copy of notice of completion, Doc. No. 2026-0081562 | 09/14/2026
09/22/2026 | 7022 1670 0002 3391 4711 | Dunmore-Kettle Builders | Rocklin | Notice that payment application 8 is held | 09/23/2026
09/24/2026 | 7022 1670 0002 3391 4738 | Sorensen Landscape Co | Granite Bay | Punch list on plant replacement, final invoice held | 09/28/2026
Returned mail, job file 2210-B
DATE_RETURNED | ARTICLE_NO | REASON
09/29/2026 | 7022 1670 0002 3391 4399 | Unclaimed, returned to sender